## Punch List
Construction Punch List
Item Number | Task Location | Task Description | POC | Priority | Due Date | Status
1 | Master Bedroom | Multiple paint marks on wall and floor; touch up and clean up | Contractor A | Medium | 2023-10-02 | Complete
2 | Kitchen | Stove backsplash isn't installed; install | Designer A | Medium | 2023-10-03 | Not Started
3 | Bathroom #1 | Cracked tile and mirror on bathroom floor, caused by faulty products; replace | Contractor A | High | 2023-10-04 | In Progress
4 | Bathroom #1 | Lights won't turn on; rewire | Electrician A | High | 2023-10-05 | In Progress
5 | Yard | Pile of bricks/materials; extra; pick up and transport to next site | Contractor C | Low | 2023-10-06 | Complete